## Pre-populated risk register
Operational risk assessment In Respect Of : Filming on campus
| Date created |  | By: | Review cycle | annual
| Last reviewed |  | Date: | Next renewal due on or by
ID | This is what we aim to achieve | These are the areas we worry about | This is what could happen if things go wrong | This is what we are doing to stop it going wrong | Risk Level H, M, L | Has this reduced the risk to an acceptable level? | Additional measures
1 | Compliance: we meet all legal, contractual and University obligations | No contractual agreement between visiting film company and University | Financial loss to University in the event of a third party making a claim and there is no agreement in place to transfer liability to the film company | 1. Permission of College Manager/Head of Department obtained. 2. Follow filming on campus protocol including obtaining a signed agreement with the film company | L
2 | Compliance: we meet all legal, contractual and University obligations | Unauthorised filming of staff, students and visitors in the background. | Claims for breach of privacy / data protection laws / CDPA 1988 brought against the University. | 1. Participants and individuals who are known will be in the background will be asked to sign a consent form. 2. Erect signage warning of filming in the immediate area. 3. Be prepared to interrupt filming if complaint received. | L | Y
3 | Financial: We remain within budget, assets are secure | Insufficient insurance cover held by film company | Film company unable to meet a financial liability which would have been covered by their insurance if in place leading to possible claim against the University by third party. | Request details of insurance held by film company to evidence sufficient level of cover. | L | Y
4 | Publicity/reputation: Our reputation is enhanced by this activity | Film subject/quality does not reflect well on the University. Breach of privacy/data protection, copyright or use of intellectual property or confidential information without permission | 1. Adverse press reporting. 2. Public apology required by the University. | 1. [Press Office review subject material before filming activity takes place?]. 2. Participants offered PR training prior to taking part if inexperienced. | L | Y
5 | Service provision: We are able to complete this activity on time and our normal services are not adversely affected by this activity | Filming causes disruption to normal University activities | Complaints by students and other visitors | Check [with Event Exeter?] area to be used for filming is suitable and not in use for other purposes. | L | Y
6 | H&S Safety of participants and third parties is ensured | Injury to participants in filming. Injury to spectators/other users of the campus | 1. Filming disrupted. 2. Claim against the University for injury. | 1. Check with the [Press Office?] for suitable sites to use for filming. 2. Request copy of risk assessment from film company (type of equipment, trailing wires etc.). 3. Complete H&S risk assessment for activity. 3. [Advise Estate Patrol Office of filming event?]. | L | Y
7 | Participant experience: Participants have a positive experience from this activity. | Filming protocol not followed due to perceived bureaucracy. | Inefficient use of academic/senior staff time in organising the event. | 1. Guidance note/protocol written with input from multiple departments. 2. Feedback sought from protocol users. 3. Protocol reviewed [annually?] | L | Y
Risk calculator - use the following as a guide to determining the level of risk
| Risk category | What would happen | Why
| High (H) | Activity has to cease | Death, serious injury
Serious non-compliance with law/regulations/contract terms
Level of reputation damage, including serious complaint from student(s)
Level of financial loss (> 20% budget)
| Medium (M) | Activity adversely affected - may be curtailed or still completes | Injury but contained to one person and not serious
Breach of law/regulations/contract terms or University policy identified but not serious
Reputation damage but short term and not serious, including complaints from student(s)
Financial loss but this can be met by department or College (between 5% and 19% of budget)
| Low (L) | Activity completes but not all desired outcomes achieved | Minor injury e.g. cuts, bruises
University policy not followed but not subject to disciplinary
Minor damage to reputation
Minor complaint(s) from students
Budget overspend but met by department only (< 5% of budget)

## Guidance notes
Management of Outcomes – completing an operational risk assessment <<Guidance Note>>
Whether you are undertaking a research project on your own or the organiser of an event such as a fieldtrip or similar group activity, you will have overall responsibility for the success of the project/event. The following approach has been developed to assist you in meeting your responsibilities following a straightforward system that is not time consuming.
Step 1
Desired outcomes - The starting point is simply in stating the desired outcome(s) that you want to achieve. Doing this makes the other steps easier to complete.
Step 2
Identify the key areas of concern - The purpose of this stage is to start to focus the mind. The key areas of concern have already been identified for you as:
Area of concern | Example
Compliance with laws, regulations, contracts , policies and procedures | Trespass - contravention may result in fines, conviction for an offence or disciplinary action
Financial | Unforeseen costs could affect the ability to complete the activity
Reputation | Injury to student receives national press coverage focusing on who was at fault
Health & Safety | Member of staff injured and unable to drive minibus back to University
Student/staff experience | Complaints received from students that fieldtrip was poorly managed
Step 3 – The risk assessment
Here we record details of:
1. Adverse events we worry about. Note, these are not just limited to health & safety risks.
2. What can be done to stop things going wrong.
3. Assessment of the level of risk (High, Medium, Low)
Step 4 - review your entries
You have now completed the risk assessment.
Step 5
Make it live - The risk assessment is of no use unless you put into practice the actions you have identified to reduce the risk of things going wrong. The following principles are also very important:
Share it – risks that may affect participants must be brought to their attention. This is best done by briefing participants on the main risks – this can be verbal but is better done in written form.
Make a record – please keep written records of actions you take before, during or after the activity that affect this risk assessment. You may need to recall your actions should an adverse event occur, however, generally a brief note is all that is required to jog the memory at a later date. Remember to jot down the timing of any significant event.
Step 6
Insurance - If you did not identify any additional High or Medium level risks at Step 3, your activity will be covered. If you have identified additional risks, it is very likely that insurance cover is available, please refer to your College or Legal & Insurance Services. If you are travelling abroad, you should still complete the online travel notification form.
Finally, we are always happy to answer any queries. Please contact us by phone: 3087; or by email: insurance@exeter.ac.uk